## Overall Metrics
/Proyectos/PSP2.1 Programa7
PSP2.1 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 21.1 | 21.1 | 16.6
Planned Time | 5:56 |  | 27:41
Actual Tiempo |  | 5:59 | 41:41
CPI (Cost-Performance Index) |  |  | 0.81
% Reuse | 0% | 0% | 0%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 12.3 | 0 | 10.1
Total Defects/KLOC or equivalent | 58.2 | 0 | 47.6
Yield % | 72.7% | #DIV/0! | 72.7%
Code Review Rate | 728 | 291 | 472
% Appraisal COQ | 6.21% | 14.5% | 7.4%
% Failure COQ | 15% | 7.52% | 14%
COQ A/F Ratio | 0.41 | 1.93 | 0.53
PQI | 0.01 | 0.34 | 0.03
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 09:46 AM el 29/04/2017